## Slide 1
Steering Committee
◆
Northwind 2027 — September 2026
Northwind 2027 — September 2026
Internal decision team — Steering Committee — September 2026

## Slide 2
Programme Status
◆
Blended OEE up 2.1pt vs.
Blended OEE up 2.1pt vs. Q2 baseline (61.4% → 63.5%)
◆
Warehouse Automation Wave 1 on track for…
Warehouse Automation Wave 1 on track for Leeds go-live in November
◆
Predictive Maintenance sensors installed on 60% of…
Predictive Maintenance sensors installed on 60% of critical assets
Internal decision team — Steering Committee — September 2026
INTERNAL · Consultify · 2/6

## Slide 3
Warehouse Automation Update
◆
Conveyor and pick-to-light installation is complete on…
Conveyor and pick-to-light installation is complete on 2 of 4 zones. Operator training starts week of 21 September.
Internal decision team — Steering Committee — September 2026
INTERNAL · Consultify · 3/6

## Slide 4
Predictive Maintenance Update
◆
Rotherham Line 3 sensors are live and…
Rotherham Line 3 sensors are live and streaming vibration data. First predictive alert caught a bearing failure 9 days before it would have stopped the line.
Internal decision team — Steering Committee — September 2026
INTERNAL · Consultify · 4/6

## Slide 5
Risks & Decisions Needed
◆
Shopfloor Wi-Fi upgrade at Rotherham is 3…
Shopfloor Wi-Fi upgrade at Rotherham is 3 weeks behind — needed before digital twin pilot can scale
◆
Decision needed
Decision needed: approve Energy Efficiency Programme budget (£410k) — see Digital Roadmap
Internal decision team — Steering Committee — September 2026
INTERNAL · Consultify · 5/6

## Slide 6
Next Steps
◆
Confirm Rotherham Wi-Fi upgrade timeline by 20…
Confirm Rotherham Wi-Fi upgrade timeline by 20 September
◆
Steering Committee decision on Energy Efficiency Programme…
Steering Committee decision on Energy Efficiency Programme budget
◆
Next review
Next review: 8 October 2026
Internal decision team — Steering Committee — September 2026
INTERNAL · Consultify · 6/6